Learning and Teaching Development Project Final Report

| Project: | Videos on the use of software packages for Economics |
| --- | --- |
| Author: | Guglielmo Volpe |
| Period covered: | 1 July 2008 to 30 June 2009 |

### Purpose of the report

To report on the final project outcomes, including the main activities of the project and how these may have differed from original plans. Project resources and links to web resources, dissemination details and any evidence of project impact should also be provided. The report should be completed by 30 June 2009.

### Main objectives/broad purposes of the project

The aim of the project is to develop a set of movies that teach students how to perform various functions within a set of commonly used economics software packages such as Excel, Stata, Eview. The specific objectives of the project are:

- To consult the economics community (through the Economics Network Associates) to identify:

- the software packages that are most commonly used with students within economics departments across the UK;

- the most common functions and tasks that students are required to perform with these software packages

- To develop about 100 videos (with audio) that explain students how to use the various functions in the most common software packages used by economists;

- To make the videos available to the economics community via the Economics Network;

- To evaluate the impact of the videos on students performance and publish the results of the research in an academic journal.

### Main activities of the project (and how and why these may have differed from original plans)

Unfortunately the project has progressed rather slowly. Since submitting the project proposal to the Economics Network, I have changed place of work and unfortunately I could dedicate little time to the project while I developed new teaching and learning material for the modules I have been asked to teach at my new University.

The main project activities that have taken place this year are the following:

- Two former colleagues, Chris Stewart and Nishaal Gooroochurn have agreed to be involved in the project and they will produce videos about Eviews and Stata respectively;

- Meetings of the ‘production team’ have taken place to agree on the content and format of the videos;

- Some videos have been produced and we hope to complete the production of all videos by September 2009;

- Unfortunately, due to time constraints it was not possible to consult the economics community to discuss the software and functions that the videos should cover. However, we hope to collect feedback after the completion of the videos and we will be prepared to produce additional videos according to specific requests.

### Outcomes of the project

- As mentioned above, the project outcomes have not yet been completed and we hope to have the videos available by September 2009.

### Available resources (including web links)

- Once the videos are produced they will be made available via the Economics Network website

### Dissemination (details of events, dates etc disseminated and planned)

- We plan to disseminate the project’s resources at the 2009 DEE conference and through the Economics Network website

### Impact (please include any evaluation data or any other evidence of the project’s impact)

- We plan to evaluate the impact of the project once all the resources have been produced.